## Script
How to Create a Project Tracker in Excel
- Basic data structure (Project/Task, Assigned To, Health, Priority, Start, End, Duration, Progress, Status)
- Creating drop down menus
- Creating color coding/other conditional formatting
- Creating hierarchy (project and task)
- Differentiating formula columns, protecting
- Gantt Chart
- Progress diagrams (use auxiliary tab for calculations)
- Dependency

## Project Tracker
|  | [Project Name Placeholder] | Complete |  | In Progress
[12 empty] | Gantt start | 2024-12-01
H | Task ID | Phase / Task | Assigned To | Health | Priority | Tgt Start | Tgt End | Dependent Task | Start | End | Duration | Progress | Status | time axis 2024-12-01 to 2025-03-01
P |  | Phase 1: Development
T | 1 | Kick off Meeting | Mary | Amber | 1 | 2024-12-14 | 2024-12-14 |  | 2024-12-14 | 2024-12-14 | 0 | 40% | In Progress
T | 2 | Gather Requirements | Emily | Green | 4 | 2024-12-16 | 2024-12-20 |  | 2024-12-16 | 2024-12-20 | 5 | 0% | Not Started
T | 3 | Review Requirements | Paul | Amber | 3 | 2024-12-16 | 2024-12-23 | 2 | 2024-12-23 | 2024-12-31 | 7 | 25% | On Hold
P |  | Phase 2: Testing
T | 4 | Functional Test Meeting | Mary | Green | 1 | 2025-01-02 | 2025-01-02 |  | 2025-01-02 | 2025-01-02 | 1 | 0% | Not Started
T | 5 | Functional Tests | Emily | Red | 4 | 2025-01-06 | 2025-01-10 |  | 2025-01-06 | 2025-01-10 | 5 | 0% | Not Started
T | 6 | UAT | Paul | Green | 3 | 2025-01-14 | 2025-01-22 |  | 2025-01-14 | 2025-01-22 | 7 | 0% | Not Started
0%
17%
67%

## Lists
Assigned To | Health | Priority | Status
Paul | Green | 1 | Complete
Mary | Amber | 2 | In Progress
Emily | Red | 3 | On Hold
|  | 4 | Not Started
Overdue

## Calculations (hidden)
Used In Progress Charts
Total Tasks | 6
Complete | 0 | 0% | 100%
In Progress | 1 | 16.67% | 83.33%
On Hold | 1 | 16.67% | 83.33%
Not Started | 4 | 66.67% | 33.33%
Overdue | 0 | 0% | 100%